## Introduction
RASCI Matrix
GovAssure
Introduction
We have developed a GovAssure specific RASCI matrix as a tool aligned to the key stages of GovAssure and its sub-component parts. This will support the identification of all the roles and responsibilities of each stakeholder involved and who will make decisions throughout GovAssure process. The template RASCI matrix is available on the GovAssure section of security.gov.uk. The RASCI matrix has been organised by the five stages of GovAssure and the sub-tasks to be completed as part of each phase. It also includes suggestions for who we would envisage being responsible, accountable, supporting, consulted or informed in each case. The template RASCI has been designed to be reasonably generic and organisations are expected to consider the roles within their organisation and adapt to fit their needs.
Sheets in this RASCI workbook
GovAssure RASCI - example | A completed example providing an indicative view of the task allocation for each Stage of GovAssure
GovAssure RASCI - blank | A version to be adapted by the organsiation to make it appropriate to their organsation and roles

## GovAssure RASCI - example
RASCI Matrix | Roles and Responsibilities
GovAssure | Responsible, Accountable, Supporting, Consulted, Informed
[Organisation name]
| INDICATIVE ROLES | Executive Management | GovAssure Accountable Officer (CISO or equivalent) | CIO / CTO | GovAssure Lead (Coordinator) | Risk Manager | Supplier / MSP | Service Owner | System Owner (or CNI Asset Owner) | Business Continuity / Disaster Recovery Representative | Engagement lead | Independent Assurance Reviewer
Name
Deliverable or Task | Status | Organisation | [8 empty] | GSG | External Party
Pre-requisites
The organisation has familiarised itself with GovAssure information on security.gov.uk / Getting Started Guide / Detailed Guidance | Not yet started | A | R | R | R | R | R | R | R | R
The organisation has issued formal communications internally related to GovAssure and has ongoing awareness raising plans | Not yet started | A | R | C | S | C | I | C | C
The organisation has begun to consider who is likely to be involved in the GovAssure process and is able to identify key roles and responsibilities (customise and update this RASCI) | Not yet started | I | A | S | R | S | C | S | S | S
The organisation has considered whether they are already using a cyber security framework that may support the completion of the GovAssure process | Not yet started |  | R | S | S | S |  | S | S | C
GovAssure Initiation / kick-off meeting | Not yet started | R A: R; C S: S; S R: R; C S: I | R
GovAssure Scoping Document familiarisation | Not yet started |  | A | R | R | R | S | R | R | C
The organisation has begun to think about existing sources of information that they may be able to utilise to support the GA process | Not yet started |  | R | S | S | S | S | R | R | C
Stage 1 - Organisational context and services
Stage 1 - Part A: Mission, Objectives and Priorities
Understand the organisation's mission, objectives and priorities and record this as part of the GovAssure Scoping Document: Stage 1 - Part A | Not yet started | A | R | S | R | S |  | C | C | C
Understand the IT & cyber operating model / infrastructure environment / supply chain | Not yet started | I | S | R | S | C | R | R | R | C
Understand and assess threat drivers, risk appetite, other factors that increase the risk of attack | Not yet started | A | R | R | S | R | C | R | R | R
Discuss and agree threat drivers for the organisation | Not yet started | I | A | A | S | R | S | R | R | C
Stage 1 - Part B: Identifying & Defining the Essential Services and determining their categorisation
Identify and understand the essential services delivered by the organisation with consideration to: - CNI - OES - Fundamental organisational outputs Utilise the Five Lens Model (Lens 1) to consider essential services and organisation functions (Lens 2). | Not yet started | A | S | S | S | C |  | R | I | C
Identify and define the essential services delivered and record these as part of the GovAssure Scoping Document: Stage 1 - Part B | Not yet started | A | S | S | S | C |  | R | I | C
Determine the importance of the essential services by considering harm and prioritisation in the event of compromise of the service | Not yet started | A | S | S | S | C |  | R | I | C
Agree the in-scope organisational essential services | Not yet started | A | S | S | S | C |  | R | I | I | C
Stage 2: In-scope systems and assignment to the Government CAF profile
Stage 2 - Part A: Identify and defining the critical systems for inclusion in-scope for GovAssure
Develop the view of the core underlying infrastructure (Lens 3 of the Five Lens Model) | Not yet started | A | R | S | S | C | S | S | R | C
Develop the view of the critical systems that underpin the essential services and functions, with considerations to: - CNI - OES - Fundamental organisational outputs (Lens 4 of the Five Lens Model) | Not yet started | A | R | S | S | C |  | S | R | C
Consider which systems are automatically in-scope for GovAssure (CNI) | Not yet started | A | R | S | S | C |  | S | R | C
Consider systems for inclusion in scope | Not yet started | A | R | S | S | C | I | S | R | C
Develop the view of the critical systems by gathering additional information on how the system is used to deliver the agreed essential service/function | Not yet started | A | R | S | S | C | S | S | R | C
Identify key sites/locations required for the delivery of the essential services and functions (Lens 5 of the Five Lens Model) | Not yet started | A | R | S | S | C | S | S | R | C
Determine the prioritisation of systems supporting the essential service/function | Not yet started | A | R | S | S | C | I | S | R | C
Develop the document scope and justification decisions | Not yet started | A | R | S | S | C | S | S | R | C
Utilise a method of prioritising systems | Not yet started | A | R | S | S | C | S | S | R | C
Agree the in-scope critical systems | Not yet started | A | R | S | S | C | S | R | R | C
Approval of in scope systems | Not yet started | A | R | S | S | C | S | R | I | I | C
Stage 2 - Part B: Develop the view of the in-scope systems
Identify system boundaries | Not yet started | A | R | R | S |  | S | C | S
Identify 3rd party dependencies | Not yet started | A | R | R | S |  | S | C | S
Understand and identify any existing sources of assurance that might affect or support inclusion in scope decisions | Not yet started | A | R | R | S | C | S | C | S
Define the target CAF profile for systems (Baseline or Enhanced) | Not yet started | A | R | R | S | I |  | I | S
Agree the assignment of target CAF profiles on a per system basis | Not yet started | A | R | R | S | I |  | I | S
Work with GSG to review and agree the Scoping Document | Not yet started | A | R | R | S | I |  | I | I | I | R
Stage 3: CAF self-assessment
Add and onboard the GovAssure Lead as "organisation lead" on WebCAF, and add other relevant "organisation user(s)" on WebCAF | Not yet started | [8 empty] | C | R | bar: R to C
Add in-scope systems on WebCAF | Not yet started | [9 empty] | S | bar: S
Add relevant "system user(s)" on WebCAF and assign to in-scope systems | Not yet started | [9 empty] | S | bar: S; S to S
Create system assessment on WebCAF | Not yet started | [9 empty] | S | bar: S; S
Take an organisation wide approach to collaboratively contributing to the CAF based on the RACSI and the key individuals identified during the Scoping Phase | Not yet started | A | R | R | S | S | S | S | S | C | I
Workshop the CAF at a Contributing Outcome level and review the underpinning IGPs | Not yet started | A | R | R | S | S | S | S | S | C | I
Review the Contributing Outcome & IGP example document | Not yet started | A | R | R | S | S | S | S | S | C | I
Review example evidence / artefacts and the worked justification and comments | Not yet started | A | R | R | S | S | S | S | S | C | I
Record answers to Contributing Outcomes and IGPs on WebCAF, providing comments on justification, logic and decision making process, along with references to supporting evidence | Not yet started | A | R | R | S | S | S | S | S | C | I
Record, track and manage supporting evidence internally | Not yet started | A | R | R | S | S | S | S | S | C | I
Conduct an internal quality assurance process over the CAF return to assess for assurance review readiness | Not yet started | A | R | R | S | S | S | S | S | C | I
Conduct an internal sign-off of the CAF as being ready for external review | Not yet started | A | R | R | S | I |  | S | S |  | I
Export final assessment from WebCAF and store internally for future reference | Not yet started | bar: A A A A A A A to S S S S S S S S; S S S S S S S S to R C C C C C C C
Status check with GSG | Not yet started | A A A A A A A: I; R R R R R R R: R; R R R R R R R: R; S S S S S S S S: S; S I I I I I I I: R
Progress assessment to independent assurance review on WebCAF | Not yet started | bar: S S S S S S S S
Schedule the independent assurance review | Not yet started | A | R | R | S | I | I | I | I |  | I | C
Stage 4 Independent assurance review
Assign Independent Assurance Reviewer(s) as "assessor(s)" to relevant assessments on WebCAF | Not yet started | [9 empty] | S | C | bar: R S
Plan / prepare for the assurance review | Not yet started | A | R | R | S | S | S | S | S | S | I | C
Agree scope / timings and key stakeholders | Not yet started | A | R | R | S | I | S | S | S | S |  | R
Work with 3rd party to complete the assurance review on WebCAF | Not yet started | A | R | R | S | S | S | S | S | S |  | R
Informal feedback and arbitration process | Not yet started | A | R | R | S | S | S | S | S | S
Export independent assessment from WebCAF for future reference if required | Not yet started | [10 empty] | R
Submit independent assessment from WebCAF | Not yet started | [9 empty] | I | R
Produce and issue draft report | Not yet started | I | S | S | S | I | C | C | S | S |  | R
Agree findings and recommendations | Not yet started | A | R | R | S | I | C | C | S | S |  | R
Provide comments on the draft report | Not yet started | A | R | R | S | I |  | S | R |  |  | C
Produce and issue final report | Not yet started | [9 empty] | I | R | bar: A to R; I
Stage 5 Final assessment and targeted improvement plan
Production of the targeted improvement plan (TIP) | Not yet started | [9 empty] | R | S | bar: R to I
Provide comments on the TIP | Not yet started | A | R | R | S | S | S | R | R | S | I
Monitor progress of agreed actions | Not yet started | A | R | R | S | S | S | R | R | S | I | I
R | Responsible | A A: Assigned to complete the task or deliverable.
A | Accountable | A A: Has final decision-making authority and accountability for completion. Only 1 per task.
S | Supporting | A A: Provides support during implementation.
C | Consulted | A A: An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | A A: Must be informed after a decision or action.

## Org Internal RASCI
RASCI Matrix | Roles and Responsibilities
GovAssure | Responsible, Accountable, Supporting, Consulted, Informed
[Organisation name]
| ROLES | Executive Management | GovAssure Accountable Officer (CISO or equivalent) | CIO / CTO | GovAssure Lead (Coordinator) | Risk Manager | Supplier / MSP | Service Owner | System Owner (or CNI Asset Owner) | Business Continuity / Disaster Recovery Representative | Engagement lead | Independent Assurance Reviewer
Name
Deliverable or Task | Status | Organisation | [8 empty] | GSG | External Party
Pre-requisites
The organisation has familiarised itself with GovAssure information on security.gov.uk / Getting Started Guide / Detailed Guidance | Not yet started
The organisation has issued formal communications internally related to GovAssure and has ongoing awareness raising plans | Not yet started
The organisation has begun to consider who is likely to be involved in the GovAssure process and is able to identify key roles and responsibilities (customise and update this RASCI) | Not yet started
The organisation has considered whether they are already using a cyber security framework that may support the completion of the GovAssure process | Not yet started
GovAssure Initiation / kick-off meeting | Not yet started
GovAssure Scoping Document familiarisation | Not yet started
The organisation has begun to think about existing sources of information that they may be able to utilise to support the GA process | Not yet started
Stage 1 - Organisational context and services
Stage 1 - Part A: Mission, Objectives and Priorities
Understand the organisation's mission, objectives and priorities and record this as part of the GovAssure Scoping Document: Stage 1 - Part A | Not yet started
Understand the IT & cyber operating model / infrastructure environment / supply chain | Not yet started
Understand and assess threat drivers, risk appetite, other factors that increase the risk of attack | Not yet started
Discuss and agree threat drivers for the organisation | Not yet started
Stage 1 - Part B: Identifying & Defining the Essential Services and determining their categorisation
Identify and understand the essential services delivered by the organisation with consideration to: - CNI - OES - Fundamental organisational outputs Utilise the Five Lens Model (Lens 1) to consider essential services and organisation functions (Lens 2). | Not yet started
Identify and define the essential services delivered and record these as part of the GovAssure Scoping Document: Stage 1 - Part B | Not yet started
Determine the importance of the essential services by considering harm and prioritisation in the event of compromise of the service | Not yet started
Agree the in-scope organisational essential services | Not yet started
Stage 2: In-scope systems and assignment to the Government CAF profile
Stage 2 - Part A: Identify and defining the critical systems for inclusion in-scope for GovAssure
Develop the view of the core underlying infrastructure (Lens 3 of the Five Lens Model) | Not yet started
Develop the view of the critical systems that underpin the essential services and functions, with considerations to: - CNI - OES - Fundamental organisational outputs (Lens 4 of the Five Lens Model) | Not yet started
Consider which systems are automatically in-scope for GovAssure (CNI) | Not yet started
Consider systems for inclusion in scope | Not yet started
Develop the view of the critical systems by gathering additional information on how the system is used to deliver the agreed essential service/function | Not yet started
Identify key sites/locations required for the delivery of the essential services and functions (Lens 5 of the Five Lens Model) | Not yet started
Determine the prioritisation of systems supporting the essential service/function | Not yet started
Develop the document scope and justification decisions | Not yet started
Utilise a method of prioritising systems | Not yet started
Agree the in-scope critical systems | Not yet started
Approval of in scope systems | Not yet started
Stage 2 - Part B: Develop the view of the in-scope systems
Identify system boundaries | Not yet started
Identify 3rd party dependencies | Not yet started
Understand and identify any existing sources of assurance that might affect or support inclusion in scope decisions | Not yet started
Define the target CAF profile for systems (Baseline or Enhanced) | Not yet started
Agree the assignment of target CAF profiles on a per system basis | Not yet started
Work with GSG to review and agree the Scoping Document | Not yet started
Stage 3: CAF self-assessment
Add and onboard the GovAssure Lead as "organisation lead" on WebCAF, and add other relevant "organisation user(s)" on WebCAF | Not yet started
Add in-scope systems on WebCAF | Not yet started
Add relevant "system user(s)" on WebCAF and assign to in-scope systems | Not yet started
Create system assessment on WebCAF | Not yet started
Take an organisation wide approach to collaboratively contributing to the CAF based on the RACSI and the key individuals identified during the Scoping Phase | Not yet started
Workshop the CAF at a Contributing Outcome level and review the underpinning IGPs | Not yet started
Review the Contributing Outcome & IGP example document | Not yet started
Review example evidence / artefacts and the worked justification and comments | Not yet started
Record answers to Contributing Outcomes and IGPs on WebCAF, providing comments on justification, logic and decision making process, along with references to supporting evidence | Not yet started
Record, track and manage supporting evidence internally | Not yet started
Conduct an internal quality assurance process over the CAF return to assess for assurance review readiness | Not yet started
Conduct an internal sign-off of the CAF as being ready for external review | Not yet started
Export final assessment from WebCAF and store internally for future reference | Not yet started
Status check with GSG | Not yet started
Progress assessment to independent assurance review on WebCAF | Not yet started
Schedule the independent assurance review | Not yet started
Stage 4 Independent assurance review
Assign Independent Assurance Reviewer(s) as "assessor(s)" to relevant assessments on WebCAF | Not yet started
Plan / prepare for the assurance review | Not yet started
Agree scope / timings and key stakeholders | Not yet started
Work with 3rd party to complete the assurance review on WebCAF | Not yet started
Informal feedback and arbitration process | Not yet started
Export independent assessment from WebCAF for future reference if required | Not yet started
Submit independent assessment from WebCAF | Not yet started
Produce and issue draft report | Not yet started
Agree findings and recommendations | Not yet started
Provide comments on the draft report | Not yet started
Produce and issue final report | Not yet started
Stage 5 Final assessment and targeted improvement plan
Production of the targeted improvement plan (TIP) | Not yet started
Provide comments on the TIP | Not yet started
Monitor progress of agreed actions | Not yet started
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Supporting | Provides support during implementation.
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed | Must be informed after a decision or action.

## Org RASCI for GSG
Please fill in the below and add additional rows as needed
| Stakeholder | Email | Job title
Stage 1
Stage 2
Stage 3
Stage 4
Stage 5

## Sheet1 (hidden)
Option
Not yet started
In progress
Complete