## RASCI matrix example
Cyber Assessment Framework for local government
Roles and responsibilities RASCI matrix example
Plan your schedule and identify who needs to be involved in each stage of the Cyber Assessment Framework for local government.
R | Responsible | Will complete the task or deliverable
A | Accountable | Has final decision-making authority for completion
S | Supporting | Provides support during implementation
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action
I | Informed | Must be told once a decision made / action taken
RASCI matrix example
This is an example of how you might use the template on the next tab to allocate tasks for each stage.
Role
Task | Project manager | Collaborator | Quality assurer | Systems mapper | Approver | Independent assurance reviewer (External)
Prepare for the CAF (onboarding)
Understand what the CAF involves | R | R | R | R | R
Plan your schedule | R | S | I | S | A | I
Identify key roles and responsibilities | R | S | S | S | A
Book in time to collaborate | R | S | I | S
Understand what independent assurance involves and establish contact with your independent assurer | R | R | R | R | R | R
Establish an approach for securing your assessment and evidence | R |  |  | S |  | I