## RASCI matrix template
Cyber Assessment Framework for local government
Template: Roles and responsibilities RASCI matrix
Use this tool to plan your schedule and identify who needs to be involved in each stage of the Cyber Assessment Framework for local government.
R | Responsible | Will complete the task or deliverable
A | Accountable | Has final decision-making authority for completion
S | Supporting | Provides support during implementation
C | Consulted | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action
I | Informed | Must be told once a decision made / action taken
Role
Task | CAF lead | Collaborator | Quality assurer | Systems mapper | Approver | Independent assurance reviewer (External)
Prepare for the CAF (onboarding)
Understand what the CAF involves
Plan your schedule
Identify key roles and responsibilities
Book in time to collaborate
Understand what independent assurance involves and establish contact with your independent assurer
Establish an approach for securing your assessment and evidence
Setting the scope
Confirm your organisation's strategic context
Identify your essential services
Identify your critical systems
Prioritise your critical systems
Share your strategic context, essential services and critical systems with your independent assurer and updated work schedule for feedback
Finalise your scoping document
Submit your scoping document to MHCLG
Self-assessment of your organisation
Understand the objectives, principles, contributing outcomes and indicators of good practice relating to self-assessing your organisation
Establish who needs to be involved for each contributing outcome
Collectively review each contributing outcome and relevant indicators of good practice
Identify and collate documents as evidence to support your self-assessment
Self-assess against each contributing outcome and relevant indicators of good practice
Check your self-assessment is ready for independent assurance review
Check your self-assessment for quality and accuracy
Finalise your self-assessment
Assure and develop an improvement and implementation plan for your organisation assessment
Share your self-assessment with your independent assurer
Provide your independent assurer with access to evidence supporting your self-assessment
Collectively address any clarifications raised by your independent assurer
Review the assurance report and discuss any feedback with your independent assurer
Share findings from the assurance report with senior leadership and relevant stakeholders
Use your assurance report to create your improvement and implementation plan
Share your improvement and implementation plan with your independent assurer for feedback
Finalise your assured assessment and improvement and implementation plan
Submit to MHCLG your assured assessment and improvement plan
Self-assessment of your critical system(s)
Complete architecture discovery and architecture scoping
Map your critical system architecture
Share your critical system architecture map with your independent assurer for feedback
Finalise your critical system architecture map
Understand the objectives, principles, contributing outcomes and indicators of good practice relating to self-assessing your organisation
Establish who needs to be involved for each contributing outcome
Collectively review each contributing outcome and relevant indicators of good practice
Identify and collate documents as evidence to support your self-assessment
Self-assess against each contributing outcome and relevant indicators of good practice
Check your self-assessment is ready for independent assurance review
Check your self-assessment for quality and accuracy
Finalise your self-assessment
Assure and develop an improvement plan for your critical system assessment
Share your self-assessment with your independent assurer
Provide your independent assurer with access to evidence supporting your self-assessment
Collectively address any clarifications raised by your independent assurer
Review the assurance report and discuss any feedback with your independent assurer
Share findings from the assurance report with senior leadership and relevant stakeholders
Use your assurance report to create your improvement and implementation plan
Share your improvement and implementation plan with your independent assurer for feedback
Finalise your assured assessment and improvement and implementation plan
Submit your assured assessment and improvement plan to MHCLG