## Example schedule
Cyber Assessment Framework for local government schedule
This shows how you might plan to assess your council's cyber resilience.
Some activities can be done at the same time - for example, your system mappers can start the architecture mapping for your critical systems while your collaborators and project manager complete the organisational self-assessment.
Remember to consider annual leave and other business activities that might affect capacity.
These time estimates should be used as a guide and might vary depending on the size of your council.
Stage | About | Who this involves | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26
Onboarding and preparing | Understanding what the CAF is, what this means for your council, planning your schedule and who needs to be involved. | - CAF project manager (lead) - CAF approver (SLT) - Advocate | Week 1: Plan about 3 weeks to complete onboarding (estimated 45 hours in total)
Setting the scope | Discussing organisational strategic context, identifying your essential services and critical systems | - CAF project manager (lead) - CAF collaborators | Week 4: Plan about 4 weeks to set your scope (estimated 35 hours in total)
Self-assessment of your organisation | Completing the self-assessment of your organisation including gathering documentation to use as evidence, and quality assurance checks before submission. | - CAF project manager (lead) - CAF collaborators Before submitting: - Quality assurer - CAF approver (SLT) | Week 8: Plan about 4 weeks the complete the self-assessment of your organisation (estimated 35-40 hours in total)
Independent assurance and improvement plan for your organisational assessment | Collaborating with your independent assurers, using prioritised feedback to create your improvement and implementation plan. | - CAF project manager (lead) - CAF collaborators - System mapper - Quality assurer - CAF approver (SLT) | Week 13: Plan about 3 weeks for your independent assurance review, and 3 weeks to complete and confirm your improvement and implementation plan (estimated 15-20 hours in total)
Critical system architecture mapping (x1) | Undertaking network and system discovery, creating architecture documentation of your critical system. | - System mapper - CAF collaborators | Week 9: Plan about 6 weeks to complete the architecture mapping for 1 x critical system (estimated 20 hours in total)
Self-assessment of your critical system (x1) | Completing the self-assessment of your critical systems including gathering documentation to use as evidence, and quality assurance checks before submission. | - System mapper - CAF collaborators Before submitting: - Quality assurer - CAF approver (SLT) | Week 15: Plan about 6 weeks to complete the self-assessment for 1 x critical system (estimated 60 hours in total)
Independent assurance and improvement plan for your critical systems assessment | Collaborating with your independent assurers, using prioritised feedback to create your improvement and implementation plan. | - CAF project manager (lead) - CAF collaborators - System mapper - Quality assurer - CAF approver (SLT) | Week 21: Plan about 3 weeks for your independent assurance review, and 3 weeks to complete and confirm your improvement and implementation plan (estimated 15-20 hours in total)