## Template schedule
Cyber Assessment Framework for local government schedule
Use this template to plan how you will assess your council's cyber resilience.
You may prefer to use any existing project management tools embedded in your council.
Stage | About | Who will be involved | Week 1 [Add date] | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26
Onboarding and preparing | Understanding what the CAF is, what this means for your council, planning your schedule and who needs to be involved. | [Add names of team members identified to be involved]
Setting the scope | Discussing organisational strategic context, identifying your essential services and critical systems
Self-assessment of your organisation | Completing the self-assessment of your organisation including gathering documentation to use as evidence, and quality assurance checks before submission.
Independent assurance and improvement plan for your organisational assessment | Collaborating with your independent assurers, using prioritised feedback to create your improvement and implementation plan.
Critical system architecture mapping (x1) | Undertaking network and system discovery, creating architecture documentation of your critical system.
Self-assessment of your critical system (x1) | Completing the self-assessment of your critical systems including gathering documentation to use as evidence, and quality assurance checks before submission.
Independent assurance and improvement plan for your critical systems assessment | Collaborating with your independent assurers, using prioritised feedback to create your improvement and implementation plan.